## Slide 1
Organization Restructuring Milestone Dashboard
1 January 2019
Partnerships Department — 100% Complete
Monitoring & Evaluation Department — 66% Complete
Program Laws 1.0 — 0% Complete
Education Department — 100% Complete
Human Resources — 50% Complete

## Slide 2
Human Resources
50% Complete

## Slide 3
Human Resources Dashboard
25%
Hire a contract HR professional to support
June
Notes
100%
Define Core Values
March
75%
Review employment benefit packages
June
0%
Conduct a survey on employee happiness
July

## Slide 4
Education Department Restructuring
Program development is created by the Education Department.
100% Complete

## Slide 5
Education Department Dashboard
Notes
100%
Redefine & restructure programmatic development in the Education Department.
February
100%
Pre-Assessment and Project Management are consolidated into the Education Department.
February
100%
Education Department controls all budgeting.
February

## Slide 6
Program Laws 1.0
Bringing programs forward to truly address a school’s needs.
0% Complete

## Slide 7
Program Laws 1.0 Master Dashboard
0%
ED creates Program Laws Version 1
February
0%
ED creates Program Laws Version 2
February
0%
Vote on Program Laws
March
Notes

## Slide 8
Monitoring & Evaluation Department
Assessing all schools, producing quality reporting ,and providing support to teachers.
66% Complete

## Slide 9
Program Laws 1.0 Master Dashboard
100%
M&E team members commit schedule.
February
100%
Confirm with our partner about schedule.
February
0%
Implement the new plan.
March
Notes

## Slide 10
Partnerships Department Restructuring
A focus on long-term win-win partnerships.
100% Complete

## Slide 11
Partnerships Department Dashboard
Notes
100%
Fundraising Department has been relaunched as the Partnerships Department.
February
100%
Partnerships Department has received Program Laws 1.0 and ED has trained the Shanghai team members on new laws.
March
100%
Partnership Department has provided external document templates with design language to ED.
February